## Test
KEY: | completed
completed by Jan 2nd
unknown amount of work, TBD
Group Assignment | Section | Responsible | Tests within Group | Notes
tnvme/dnvme general notes/concerns | n/a
|  |  | General Error Check Function: Single fucntion which checks everywhere for an error state that may have occurred during the test run. Not sure if we need one in dnvme and tnvme or can we just have one in dnvme? | Check PCI STS reg
check PCI PXCAP-PXDS if supported
check PCI PXCAP-PXLS if supported
check PCI AERCAP-AERUCES if supported
check PCI AERCAP-AERUCESEV if supported
NOTE: For AERUCES & AERUCESEV remember to check the appropriate mask register, if an error is reported and it is suppose to be masked then the error reporting is a subsequent failure as well.
API Development Tasks | n/a
|  |  | Data Structure Creation | (18 hrs)
|  |  | Add skiptest support suggested during preso | (24 hrs)
|  |  | IOCTL_GET_DRIVER_METRICS | (12 hrs)
|  |  | IOCTL_GET_Q_METRICS | (12 hrs)
|  |  | IOCTL_CREATE_ADMIN_Q | (24 hrs)
|  |  | IOCTL_ALLOCATE_SQ | (18 hrs)
|  |  | IOCTL_ALLOCATE_CQ | (18 hrs)
|  |  | IOCTL_SEND_64B_CMD | TASK#0: (36 hrs) Create PRP list logic as a discrete function TASK#1: (6 hrs) Unique ID support and error checking TASK#2: (12 hrs) Adding overhead to handle cmds as they arrive
|  |  | Intel PDT approval (review comments) | (12 hrs)
|  |  | Making Qemu more generic across different endianess architectures | (12 hrs)
|  |  | IOCTL_RING_SQ_DOORBELL | (18 hrs)
|  |  | IOCTL_REAP_INQUIRY | (18 hrs)
|  |  | Design ISR Support Infrastruture | (12 hrs)
|  |  | IOCTL_REAP | Task#0: (24 hrs) Algorithm to reap on ACQ Task#1: (12 hrs) Algorithm to reap on CQ's Task#2: (12 hrs) Cmd parsing overhead
|  |  | IOCTL_DEVICE_STATE | Task#0: (12 hrs) ST_ENABLE support Task#1: (18 hrs) ST_DISABLE support Task#2: (12 hrs) ST_DISABLE_COMPLETELY support
|  |  | ISR Design: ISR Routine | See design notes
|  |  | ISR Design: IOCTL_SET_IRQ | See design notes
|  |  | ISR Design: Additions to IOCTL_CREATE_ADMIN_Q | See design notes
|  |  | ISR Design: Additions to IOCTL_SEND_6B_CMD | See design notes
|  |  | ISR Design: Additions to IOCTL_REAP_INQUIRY | See design notes
|  |  | ISR Design: Additions to IOCTL_REAP | See design notes
tnvme general notes/concerns | n/a | In the following "if supported" means if a generic device supports the page then do the action. It does not mean if QEMU decides to support or not.
Logging: The framework provides class wrapper around a purely virtual method a child must implement. The wrapper should log the short/long description at test start, and a default PASS/FAIL status in case the child forgets.
Rule: During tnvme launch an initial check of PMCAP PCI reg must occur to verify in full power, else error out. Most ops are disabled in lower power states, do not check between successive tests, just at the start of all when app launches.
|  |  | Add Cmd Line Option: to cleanup after each test case; meaning to reset sticky errors between individual tests. Tnvme can run and ignore errors, clearing sticky errors between stops the propagation of the same error to subsequent tests. | PCI STS reg, PCI PXCAP-PXDS if supported, PCI PXCAP-PXLS if supported, PCI AERCAP-AERUCES if supported, PCI AERCAP-AERUCESEV if supported
|  |  | Reset Sticky Errors: Always reset sticky error bits without except upon tnvme launch, i.e. before any test starts. | PCI STS reg, PCI PXCAP-PXDS if supported, PCI PXCAP-PXLS if supported, PCI AERCAP-AERUCES if supported, PCI AERCAP-AERUCESEV if supported
|  |  | Add Cmd Line Option: To return any 32b PCI register to stdout by specifying only the offset to from PCI header | From 0x00 to 0x3F
Add Cmd Line Option: To return any value from MMAP PCI address space from BAR0/BAR1, i.e. the ctrl'r register space. Specify the offset from BAR0/BAR1 and the number of bytes to return in little endian format.
Add Cmd Line Option: To execute Group Informative before any specified test. Should help identify the target.
|  |  | Add Cmd Line Option: to point to skip file list | The file is text based, CSV format and # is file comment. pairs of “<GROUP>,<TEST> #comment\n” will list those that need to be skipped. Used for tests that fail but a company may not want to see them fail, so skip them.
Group informative | n/a | Each test case should dump to its own file and overwrite each file's existing contents.
|  |  | Dump PCI address space | Everything in PCI header, All capabilities pages, everything in raw hex output.
|  |  | Dump ctrl'r address space | Everything except doorbell registers
Group PCI registers | 2 | Validate the RO fields cannot be written
Validate ctrl'r reset does NOT affect these registers
Validate all ASCII fields only contain chars 0x20 to 0x7E, never NULL
Validate writing reserved bits should be ignored
|  |  | Registers within PCI header | Offset 0x00 thru 0x3F
PMCAP
|  |  | MSICAP | Optional, test if device supports, not whether QEMU supports it or not
|  |  | MSIXCAP | Optional, test if device supports, not whether QEMU supports it or not
|  |  | PXCAP | Optional, test if device supports, not whether QEMU supports it or not
|  |  | AERCAP | Optional, test if device supports, not whether QEMU supports it or not
|  |  | Mandatory capabilities present | Search to see if all the mandatory pages are present.
Group controller registers MMAP | 3 | Validate the RO fields cannot be written
Validate ctrl'r reset does NOT affect these registers
Validate all ASCII fields only contain chars 0x20 to 0x7E, never NULL
Validate writing reserved bits should be ignored
Controller capabilities
Version
Interrupt mask set
Interrupt mask clear
Controller status
Admin Q attributes
Admin submission Q base addr
Admin completion Q base addr
|  |  | Submission Q y tail doorbell | doorbell reg reads are undefined, writing an unallocated Q has undefined results.
|  |  | Completion Q y head doorbell | doorbell reg reads are undefined, writing an unallocated Q has undefined results.
Group Basic Initialization | 7 | Controller initialization and basic duties using polling and interrupts to reap CE's (Completion Elements)
|  |  | TestCreateACQASQ() | Create memory, issue cmd to hdw, sset CC.AMS, CC.MPS, CC.CSS, enable ctrlr.
|  |  | TestIdentifyCtrlrData() | Issue identify cmd to ASQ and request controller data
|  |  | TestIdentifyNmspData() | Issue identify cmd to ASQ and request all namespace data
|  |  | FormatMedia | Issue admin cmd to format media to a default format for the following tests.
|  |  | TestCreateIOCQContigPoll() | Create a contiguous IOCQ and poll for CE's
|  |  | TestCreateIOSQContig() | Create a contiguous IOSQ and assoc with prev IOCQ
|  |  | TestNvmeWriteContig() | Write 16KB to the 1st LBA using the contiguous IO Q's and pattern A
|  |  | TestNvmeReadContig() | Read16KB from the 1st LBA using the contiguous IO Q's and verify pattern A
|  |  | TestCreateIOCQNoncontigPoll() | Create a non-contiguous IOCQ and poll for CE's
|  |  | TestCreateIOSQNoncontig() | Create a non-contiguous IOSQ and assoc with prev IOCQ
|  |  | TestNvmeWriteNoncontig() | Write 16KB to the 2nd LBA using the contiguous IO Q's and pattern B
|  |  | TestNvmeReadNoncontig() | Read 16KB from the 1st LBA using the non-contiguous IO Q's and verify pattern B
|  |  | TestCreateIOCQContigIrq() | Create a contiguous IOCQ and use IRQ's for CE's
|  |  | TestCreateIOSQContig() | Create a contiguous IOSQ and assoc with prev IOCQ
|  |  | TestNvmeWriteContig() | Write 16KB to the 1st LBA using the contiguous IO Q's and pattern A
|  |  | TestNvmeReadContig() | Read 16KB from the 1st LBA using the contiguous IO Q's and verify pattern A
|  |  | TestCreateIOCQNoncontigIrq() | Create a non-contiguous IOCQ and use IRQ's for CE's
|  |  | TestCreateIOSQNoncontig() | Create a non-contiguous IOSQ and assoc with prev IOCQ
|  |  | TestNvmeWriteNoncontig() | Write 16KB to the 2nd LBA using the contiguous IO Q's and pattern B
|  |  | TestNvmeReadNoncontig() | Read 16KB from the 1st LBA using the non-contiguous IO Q's and verify pattern B
Group resets | 7 | PCI functional and controller resets only
|  |  | Functional reset: All I/O submission Q deleted | see if the admin Q states it is size=0
|  |  | Functional reset: All I/O completion Q Deleted | see if the admin Q states it is size=0
|  |  | All resets: Cause Async Events to abort | All outstanding async events should be aborted.
|  |  | All resets: Controller enters idle state | CSTS.RDY reset
|  |  | All resets: Validate reset recovery timeout. | The ctrl'r CAP.TO indicates the max time to wait for the ctrl'r to become ready.
|  |  | All resets: Controller initializes | update power up register state, CC.EX is set, CSTS.RDY should reset
|  |  | All resets: does not affect admin Q's | All admin cmds should still work after a ctrl'r reset, see CC.EN bit
|  |  | All resets: affects all I/O Q's | Create a SQ and CQ pair, cause a ctrl'r reset, attempt to create the same SQ and CQ should be allowed with identical ID's because those Q's should have been released. Should succeed.
Group general commands | 5,6
|  |  | All CID values accepted | Verify cmd DW0-CID accepts all values for a particular command.
|  |  | Issue illegal admin cmd set opcodes | all illegal values should be tested
|  |  | Issue illegal nvme cmd set opcodes | all illegal values should be tested
|  |  | W/R all namespaces | Create many namespaces, write much 2 MB data, and read back and verify while both write/read cmds specify cmd NSID value of 0xffffffff, see figure 7
|  |  | Issue cmd to undefined namespace | Create a few namepaces and then issue write to all the undefined namespace values to validate they all are rejected.
|  |  | Issue cmd LBA out of range | Want to verify figure 17 status code 80h is returned.
|  |  | Issue to much data to namespace | Create a namespace, fill it up with data, then issue 1 more command to over flow, see fugure 17 status code 81h is returned.
Group Boundary Q Conditions | 4,5,6 | These tests should equally apply and run against admin queues in each test case
These tests should equally apply and run against IO queues in each test case
|  |  | Validate new SQ, CQ pointer initial state | Should have an empty Q, issue 1 cmd, see it complete and the host now undestands the device's SQ head ptr for verification
Validate CQ phase bit as it rolls over to beginning of CQ, do for a spec'd number of CQ rollovers as passed in as a test param.
Validate SQ rollover operation, do for a spec'd number of SQ rolloevers as passed in as a test param
|  |  | Validate full state of x SQ's to 1 CQ, where x can be passed in to the test ranging from 1 to max allowed by ctrl'r | Allow CQ to fill by not reaping, this should allow the SQ to fill completely. Then start reaping and see all items complete. The number of entries should be 1 less than the size of the Q.
|  |  | Validate device's understanding of every SQ head ptr by receiving it in the corresponding CQ. Make this test complicated by associating x SQ's to 1 CQ, where x can be passed in to the test ranging from 1 to max allowed by the ctrl'r | Allow CQ to fill by not reaping, this should allow the SQ to fill completely. Then start reaping and see all items complete. The number of entries should be 1 less than the size of the Q.
Validate CQ entries are the size reported by the ctrl'r. Multiple items stacked in a CQ should suffice for this test.
Group admin Q operations | 4,5 | This class contains tests to target operations against ASQ/ACQ's. Operations can be defined to be legal or illegal against a Q.
|  |  | Insert NVME cmds into admin SQ | expect failure
|  |  | Validate SQ, CQ illegal sizes | Q to big, Q to small, num SQ != num CQ's
|  |  | Delete admin Q's | Expect error while deleting admin SQ and Admin CQ cannot be deleted using opcode 4h
|  |  | Attempt to create a SQ before a CQ by specifying an unimplemented CQ ID in the command when creating the SQ. | Expect failure.
Group I/O specific Q operations | 4,6 | test must use kernel thread to reap CQ; assume IRQL's don’t work
|  |  | Multiple(x) I/O SQ to single CQ operation, where x=(1..n), where n is max allowed num of SQ as spec'd by ctrl'r | expect success
|  |  | Multiple(x) I/O SQ to single CQ operation, where x=(n+1), where n is max allowed num of SQ as spec'd by ctrl'r | expect failure
|  |  | Insert admin cmds into an I/O SQ | expect failure
Create valid, delete CQ
Create valid, delete SQ
|  |  | Validate virtual contigous SQ and CQ's | If ctrl'r reg CAP.CQR=0, then writes to virtually contigous mem is possible, then the kernel mod should use approp. Alloc func to create CQ and SQ's which are not physically contiguous and attempt to write/read/verify various namespaces.
|  |  | Validate doorbell stride value | Create a system with space between doorbell (CAP.DSTRD) registers and validate both the SQ and CQ work. Test multiple SQ to CQ's in operation in parallel and have each SQ take man commands, maybe allow the SQ to rollover at least once.
|  |  | Set Features: Number of queues | ??
|  |  | Validate I/O SQ anonymous | Pass in num of namespaces to create, if > what ctrl'r supports then test fails. Create x namespaces and 1 SQ with cmds directed to all namespaces, NSID field = 0xffffffff. Read back data and valdiate the data was dispatched to proper namespace.
|  |  | Create I/O SQ assoc to admin CQ | Specify a CQ ID=0 should be rejected because I/O Q's can't assoc to admin Q's.
|  |  | Create admin SQ via opcode 01h | Specify QID=0 should be rejected, this is not how to create a admin CQ
|  |  | Create admin CQ via opcode 05h | Specify QID=0 should be rejected, this is not how to create a admin CQ
|  |  | Create a SQ and assoc non-existent CQ | Should fail with figure 18 status code 1h
|  |  | Delete a non-exist CQ and SQ | Should fail with figure 18 status code 1h
|  |  | Assoc illegal IRQL to CQ | verify figure 18 status code 8h is returned, see fig 34, IV field. Must be an illegal value but still <= MSICAP.MC.MME or MSIXCAP.MXC.TS fields.
|  |  | non-contig SQ to contig CQ operation | If ctrl'r CAP.CQR=0, then is supports non-contigous Q's. Validate Q rolloever and write,read,validate functionality to correct namespaces. See fig 34, IEN field.
|  |  | contig SQ to non-contig CQ operation | If ctrl'r CAP.CQR=0, then is supports non-contigous Q's. Validate Q rolloever and write,read,validate functionality to correct namespaces. See fig 34, IEN field.
|  |  | non-contig SQ to non-contig CQ operation | If ctrl'r CAP.CQR=0, then is supports non-contigous Q's. Validate Q rolloever and write,read,validate functionality to correct namespaces. See fig 34, IEN field.
|  |  | Delete SQ causes abort with CQ full | Fill up CQ by not reaping completions, allow SQ to fill by keep creating new cmds, then delete the SQ and all SQ cmds should abort, even though the CQ is presently full
|  |  | Validate SQ, CQ illegal sizes | Q to big, Q to small, see CAP.MQES register, see fig 35, error code 2h
Group abort cmd | 5
|  |  | Delete SQ while populated | Allow the SQ to fill by not reaping the CQ and then delete the SQ and see the cmds aborted.
|  |  | Abort > than allowed | Attempt to abort more cmds than what the ctrl allows, see figure 18 status code 3h.
|  |  | Abort non-existent cmd-admin SQ | see figure 18 status code 4h
|  |  | Abort non-existent cmd-I/O SQ | see figure 18 status code 4h
|  |  | Abort cmd in admin SQ | Have to abort async cmds to verify it will abort
|  |  | Abort cmd in I/O SQ:CQ | Have to abort async cmds to verify it will abort
|  |  | Abort cmd in I/O multi-SQ:CQ | Have to abort async cmds to verify it will abort; multiple SQ to single CQ mapping
Group format cmd | 5
|  |  | Format an illegal type | Format to an illegal unsupported value, figure 18 status code 0x0a
Group admin set cmd syntax | 4 | ILLEGAL CMD ENTRY: of the cmd DWORDS used in the cmd, can any of them be set to illegal/unsupported values. If so, then do so and validate figure 16, status code 2h.
SET RESERVED BITS: The issueur should set all reserved bits in the SQ cmd entry, since all recipients must not check reserved fields this command should execute normally as long as the rest of the cmds fields define a valid operation
VERIFY RESERVED BITS: Any data returned by the cmd, may have reserved fields defined within, these are required to be 0. All of them.
VERIFY RANGE: Verify that the range of values reported to host are within allowed spec'd values
Abort: issue illegal cmd entry
Abort: set reserved bits
Identify: issue illegal cmd entry
Identify: set reserved bits
Identify: verify reserved bits
Identify: verify range
Log Page: issue illegal cmd entry
Log Page: set reserved bits
Log Page: verify reserved bits
Log Page: verify range
Format: issue illegal cmd entry
Format:set reserved bits
Get Features: issue illegal cmd entry
Get Features: set reserved bits
Get Features: verify reserved bits
Get Features: verify range
|  |  | Get Features: issue reserved FID | see fig 72
Set Features: issue illegal cmd entry
|  |  | Set Features: set reserved bits | remember to look for reserved bits within each FID's specialized cmd requirements
|  |  | Set Features: issue reserved FID | see fig 72
Create submission Q: issue illegal cmd entry
Create submission Q: set reserved bits
Create complettion Q: issue illegal cmd entry
Create completion Q: set reserved bits
Delete submission Q: issue illegal cmd entry
Delete submission Q: set reserved bits
Delete complettion Q: issue illegal cmd entry
Delete completion Q: set reserved bits
Async event request: issue illegal cmd entry
Async event request: set reserved bits
Async event request: verify reserved bits
Firmware activate: issue illegal cmd entry
Firmware activate: set reserved bits
Firmware download: issue illegal cmd entry
Firmware download: set reserved bits
Security send: issue illegal cmd entry
Security send: set reserved bits
Security receive: issue illegal cmd entry
Security receive: set reserved bits
Security receive: verify reserved bits
Security receive: verify range
Group user space memory manage | 4
|  |  | Metadata part of LBA | ??
|  |  | Metadata separate buffer | ??
|  |  | Multi PRP list pages | Test muliple(x) PRP list pages, where x can be passed into the test, x can range from 1 to 65535 and represents the number of 4K pages of PRP lists which is spec'd in single write cmd. The will validate the data by reading and comparing the results
|  |  | PRP(nonzero), PRP2(NULL) | Validate the PRP1(nonzero offset), PRP2(null), Issue write cmd , compare the results with read.
|  |  | PRP1(nonzero), PRP2(nonzero) | Validate the PRP1(nonzero offset), PRP2(nonzero offset), Note: PRP2 nonzero offset only possible when it points to a PRP list. Issue write cmd , compare the results with read.
|  |  | PRP1(zero), PRP2(nonzero) | Validate the PRP1(zero offset), PRP2(nonzero offset), Note: PRP2 nonzero offset only possible when it points to a PRP list. Issue write cmd , compare the results with read.
|  |  | PRP1(zero), PRP2(zero), PRP2 pts data | Validate the PRP1(zero offset), PRP2(zero offset), Note: PRP2 points to data to xfer. Issue write cmd , compare the results with read.
|  |  | PRP(zero), PRP2(zero), PRP2 pts list | Validate the PRP1(zero offset), PRP2(zero offset), Note: PRP2 points to data to a PRP list. Issue write cmd , compare the results with read.
|  |  | PRP entries > amount of transfer | Writing data but supplying more PRP entries that it takes to describe the real data could overwrite subsequent LBA's if the device doesn't correctly adhere to the actuall transfer size. Test this using write, read, verify techinques and writing from high-to-low LBA's and low-to-high LBA's.
Group NVM cmd set syntax | 6 | ILLEGAL CMD ENTRY: of the cmd DWORDS used in the cmd, can any of them be set to illegal/unsupported values. If so, then do so and validate figure 16, status code 2h.
SET RESERVED BITS: The issueur should set all reserved bits in the SQ cmd entry, since all recipients must not check reserved fields this command should execute normally as long as the rest of the cmds fields define a valid operation
VERIFY RESERVED BITS: Any data returned by the cmd, may have reserved fields defined within, these are required to be 0. All of them.
VERIFY RANGE: Verify that the range of values reported are within allowed spec'd values
Compare: issue illegal cmd entry
Compare: set reserved bits
Dataset Mgmt: issue illegal cmd entry
Dataset Mgmt: set reserved bits
Dataset Mgmt: verify reserved bits
Dataset Mgmt: verify range
Flush: issue illegal cmd entry
Flush: issue set reserved bits
Read: issue illegal cmd entry
Read: set reserved bits
Read: verify reserved bits
Write: issue illegal cmd entry
Write: set reserved bits
Write Uncorrected: issue illegal cmd entry
Write Uncorrected: set reserved bits
Group fused operations | 4,6
|  |  | 1st fused OK, 2nd fused OK, but not adjacent | 1st fused mcd is OK, 2nd fused cmd is OK, but the 2 commands are not adjacent within the SQ as is required.
|  |  | 1st fused OK, 2nd fused OK, 1st last, 2nd rollover | 1st fused mcd is OK, 2nd fused cmd is OK and both will complete OK, but make the 1st cmd the last entry in the SQ and the 2nd cmd rolls over to the 1st element in the SQ.
|  |  | 1st fused OK, 2nd fused OK, but use diff LBA | 1st fusd mcd is OK, 2nd fused cmd is OK but the 2 cmds use different LBA ranges, see proper error reported.
|  |  | 1st fused OK, 2nd fused OK, but 1st exe fails | cmd exe fails, nothing wrong with cmd format, just say write to illegal LBA.
|  |  | 1st fused OK, 2nd fused OK, but 2nd exe fails | cmd exe fails, nothing wrong with cmd format, just say write to illegal LBA.
|  |  | 1st fused OK, 2nd fused reserved bit, ring | set reserved bit in DW0-FUSE field
|  |  | 1st fused reserved bit, 2nd fused OK, ring | set reserved bit in DW0-FUSE field
|  |  | 1st fused OK, no 2nd fused, ring | Test issue 1st fused cmd with no 2nd cmd, ring doorbell
Group async operations | 5
|  |  | Set Features: temperature threshold | ??
|  |  | cause temperature event | Can be done by lowering threshold, see Set/Get Features FID=1h (arbitration) in this section
|  |  | Cause event Spare Below Threshold | cause figure 31, error status 2h
|  |  | Cause event Invalid SQ | Cause figure 30, error status 0h
|  |  | Cause illegal CQ doorbell write | Expect the error type as invalid Doorbell Write.
|  |  | Cause illegal SQ doorbell write | Expect the error type as invalid Doorbell Write.
|  |  | Cause latent event notify | Issue async event request, after some time then cause the event to trigger, verify latent completion.
|  |  | Cause immediate event notify | Cause the event to trigger, then send the async event request and verify immediate completion.
|  |  | Issue an async event and immediately reset the controller. | Expect the aycn event to be aborted.
|  |  | Verify clearing of error events | Reading the error info in log page cmd must clear this event, verify it is cleared.
|  |  | Verify clearing of smart/health events | Reading the smart/health log page cmd must clear this event, verify it is cleared.
|  |  | Verify subsequent masked events | When an event of a certain type, all events of that type are subsequenlty masked, verify this masking is occuring
|  |  | Issue > events than supported | Issue more async events that what ctrl’r supports, see figure 18 status code 5h
|  |  | Issue an async event and delete the corresponding SQ. | Expect the aycn event to be aborted.
|  |  | Issue multiple simultaneous async events. | Identify controller register specifies the limit for the total number of simultaneous async events. Expect that they are limited by this limit in the identify controller reg value.
Group firmware | 5,8
|  |  | Activate illegal firmware slot | See figure 18, status code 6h, see Identify ctrl'r data struct field FRMW
|  |  | Activate corrupted firmware slot | see fig 45, status code 7h, can corrupt by downloading in portions and injecting incorrect offsets, see fig 49, field OFST.
|  |  | Activate, then stop ctrl'r | If CC.EN goes from 1 -> 0, the firmware should activate; verify via Identify cmd FW rev field & by FW slot info log page.
|  |  | Activate, then function level reset | the firmware should activate; verify via Identify cmd FW rev field & by FW slot info log page.
|  |  | Activate, then ctrl'r level reset | the firmware should activate; verify via Identify cmd FW rev field & by FW slot info log page.
|  |  | Download valid image in portions interleaved, activate, verify | Interleave other cmds betwee the firmware download portions in the SQ
|  |  | Download valid image in portions contiguous, activate, verify | All firmware download cmds are adjacent in the SQ
Download valid image in entirety, activate, verify
|  |  | Download, don't active, stop ctrl'r | If CC.EN goes from 1 -> 0, the firmware should NOT activate; verify via Identify cmd FW rev field & by FW slot info log page.
|  |  | Download, don't activate, then function level reset | the firmware should NOT activate; verify via Identify cmd FW rev field & by FW slot info log page.
|  |  | Download, don't activate, then ctrl'r level reset | the firmware should NOT activate; verify via Identify cmd FW rev field & by FW slot info log page.
Activate different images
Group security | 5,8 | Security Send
Security Receive
TBD
Power management | 2,5,8 | Must utilize & test Set/Get Features FID=2h (power management) in this section
PCI power management
TBD
Group init & shutdown | 7 | Abort due to power loss notify; Make certain cmds are aborted due to power loss notification, see fig 16, status code 5h
Normal shutdown
Validate shutdown status; Ctrl'r register CC.SHN will be reflected in real time in ctrl'r register CSTS.SHST reigster
Abrupt shutdown
TBD
Group end-to-end checks | 4,8 | Cause guard check error; Create an end-to-end failure for the guard check, fig 21, status code 82h
Cause application check error; Create an end-to-end failure for the application check, fig 21, status code 83h
Cause reference check error; Create an end-to-end failure for thereference check, fig 21, status code 84h
TBD
Group device feature | 5 | set & get verify means set the value, read the same value back to pass
Arbitration, set & get verify
Power management, set & get verify
|  |  | LBA range type, set & get verify thru reset | These settings are suppose to be non-volatile thru a power loss, so at least test thru all types of resets.
Temp Threshold, set & get verify
Error recovery, get & set verify
|  |  | Volatile write cache, get & set verify, ifsupported | expect this to succeed
|  |  | Volatile write cache, get & set verify, if NOT supported | expect the inability to set & get this FID
|  |  | Volatile write cache, test functionality | use with read/write/flush commands.
TBD
Group log page cmd | 5
|  |  | Request illegal log page | figure 18 status code 9h
TBD
Group cmd arbitration | 4 | Must utilize & test Set/Get Features FID=1h (arbitration) in this section
|  |  | Round Robin ignore QPRIO | Validate cmd DW11.QPRIO is ignored for round robin arbitration
TBD
Group NVM cmds | 6
|  |  | Compare | ??
|  |  | Dataset Mgmt | ??
|  |  | Flush | ??
|  |  | Read | ??
|  |  | Write | ??
|  |  | Write Uncorrectable | ??
Group interrupts | 7
|  |  | MSIx handling | ??
|  |  | MSIx aggregation | ??
|  |  | MSIx masking | ??
|  |  | Set Features: interrupt coalescing | ??
|  |  | Pin based ISR | ??
|  |  | MSI ISR | ??
Poll
IRQ
Poll
IRQ